## Master Project Tracker & Delive
Column 1 | Phase | Task / Workstream | Task Type | Start Date | End Date | Status | Owner | Deliverable Ref
1 | Phase 1: Mobilization | Signing, team lead, WhatsApp, kickoff | Analysis / setup | 2026-09-15 | 2026-09-21 | Completed | All
2 | Phase 1: Mobilization | Toolforge / API access & baselines | Analysis / setup | 2026-09-15 | 2026-09-28 | In Progress | Contractor
3 | Phase 2: Data Extraction | Build pipelines (PetScan, SPARQL, Python) | Analysis / setup | 2026-09-22 | 2026-10-05 | In Progress | Contractor
4 | Phase 2: Data Extraction | Extract Wikipedia (English + Luganda) | Analysis / setup | 2026-09-22 | 2026-10-12 | Not Started | Contractor
5 | Phase 2: Data Extraction | Pull engagement analytics (Pageviews / Wikistats) | Analysis / setup | 2026-09-29 | 2026-10-12 | Not Started | Contractor
6 | Phase 3: Gap Analysis | Gap Mapping analysis | Deliverable Work | 2026-09-29 | 2026-10-26 | Not Started | Contractor | D1 (Draft Report)
7 | Phase 3: Gap Analysis | Priority Matrix & roadmap | Deliverable Work | 2026-10-13 | 2026-10-26 | Not Started | Contractor | D2 (Draft Matrix)
8 | Phase 3: Gap Analysis | Client review — D1 & D2 drafts | Client Review Window | 2026-10-27 | 2026-11-09 | Not Started | Contractor
9 | Phase 4: Commons & Bias | Commons audit | Deliverable Work | 2026-10-20 | 2026-11-16 | Not Started | Contractor | D3 (Audit Report)
10 | Phase 4: Commons & Bias | Systemic bias review (Gender, rural, subject gaps) | Analysis / setup | 2026-11-03 | 2026-11-16 | Not Started | Contractor
11 | Phase 4: Commons & Bias | Finalize D1 & D2 (post-feedback) | Deliverable Work | 2026-11-03 | 2026-11-16 | Not Started | Contractor | D1 & D2 (Final)
12 | Phase 5: Synthesis | Strategic recommendations | Deliverable Work | 2026-11-17 | 2026-11-30 | Not Started | Contractor | D4 (Recommendations)
13 | Phase 5: Synthesis | Code repository (documented) | Ongoing Workstream | 2026-09-22 | 2026-11-30 | Not Started | Contractor | D5 (Code Repo)
14 | Phase 6: Final & Handover | Assemble & submit full package | Deliverable Work | 2026-11-24 | 2026-12-07 | Not Started | Contractor | All 5 + Repo
15 | Phase 6: Final & Handover | Client final review & acceptance | Client Review Window | 2026-12-01 | 2026-12-07 | Not Started | Contractor
16 | Phase 6: Final & Handover | Revisions, presentation & publish | Handover / Final | 2026-12-08 | 2026-12-14 | Not Started | Contractor | Handover

## Key Milestones & In-Person Meet
Milestone Ref | Type | Schedule / Target Date | Description / Details | Status | Payment / Location
M1 | Payment Milestone | 2026-09-15 | Milestone Payment 1 | Completed | Payment
M2 | Payment Milestone | 2026-11-03 | Milestone Payment 2 | Not Started | Payment
M3 | Payment Milestone | 2026-12-08 | Milestone Payment 3 | Not Started | Payment
Meeting 1 | In-person Meeting | 2026-09-15 | Kickoff Meeting | Completed | Kampala
Meeting 2 | In-person Meeting | 2026-10-06 | Progress Sync | In Progress | Kampala
Meeting 3 | In-person Meeting | 2026-10-20 | Progress Sync | Not Started | Kampala
Meeting 4 | In-person Meeting | 2026-11-10 | Draft Review Sync | Not Started | Kampala
Meeting 5 | In-person Meeting | 2026-11-24 | Synthesis Review | Not Started | Kampala
Meeting 6 | In-person Meeting | 2026-12-08 | Final Handover & Presentation | Not Started | Kampala

## Abbreviations Reference
Abbreviations
1 | D1–D5: | Deliverables 1 through 5
2 | M1–M3: | Payment Milestones 1 through 3
3 | WCUGU | Wikimedia Community User Group Uganda
4 | API / SPARQL | Application Programming Interface / SPARQL Protocol and RDF Query
5
6
7
8