CONSULTANCY SERVICE AGREEMENT

UGANDA CONTENT GAP ANALYSIS PROJECT

This Consultancy Agreement (hereinafter referred to as the "Agreement") is made and entered into this 14th day of September 2026 (the "Effective Date"), by and between:

| THE CLIENT: | WIKIMEDIA COMMUNITY USER GROUP UGANDA LTD (WCUGU) A non-profit company limited by guarantee incorporated under the laws of the Republic of Uganda, having its principal office at Plot 90, Kanjokya House, Level 2, Room F2-03, Kanjokya Street, Kamwokya, P.O. Box 125498, Kampala, Uganda (hereinafter referred to as the "Client" or "WCUGU"). |
| --- | --- |
| THE CONSULTANTS: | TECHNICAL ANALYST CONSULTANCY TEAM Comprising Mr. Denis Kasozi, Mr. Caleb Nkunze, and Mr. Joseph Njoroge Njai, acting jointly and severally as independent technical analysts and Wikimedian consultants (hereinafter collectively referred to as the "Consultants" or the "Technical Team"). |

WHEREAS A.  The Client is desirous of conducting a comprehensive, data-driven Content Gap Analysis across English Wikipedia, Luganda Wikipedia (lgwiki), Wikidata, and Wikimedia Commons to evaluate Uganda-related knowledge coverage, identify systemic biases, and establish a strategic roadmap for future community editing campaigns.

WHEREAS B.  The Consultants possess specialized technical capabilities, data science expertise, domain knowledge in Wikimedia tools (including PetScan, Wikidata Query Service, Toolforge, and Wikimedia APIs), and demonstrated experience within the Ugandan Wikimedia community.

WHEREAS C.  The Parties wish to formalize their agreement setting forth the legal, technical, financial, and operational terms governing the delivery of the Uganda Content Gap Analysis Project.

CLAUSE 1.  SCOPE OF SERVICES & TECHNICAL METHODOLOGY

1.1 Scope Overview: The Consultants shall execute a thorough multi-dimensional Content Gap Analysis for Uganda-related knowledge across specified Wikimedia projects, expanding upon the initial baseline datasets (including 25,278+ articles across 2,888 categories on English Wikipedia, 43,087+ files across 1,936 categories on Wikimedia Commons, and 3M+ pageviews).

a. Wikipedia (English & Luganda): Qualitative and quantitative evaluation of Uganda-related categories, subcategories, article quality distribution (Stub 34.8%, Start 44.0%, C-Class 10.6%, B-Class 2.8%), reference citation completeness (96.8% baseline), and identification of high-viewership English articles lacking Luganda (lgwiki) translations (e.g., critical topics such as 'Menstruation Health').

b. Wikimedia Commons: Auditing total files, thematic distribution (culture, geography, history, economy, environment), photo-to-media ratio (currently ≥96% photos), and evaluating contribution impact from global campaigns such as Wiki Loves Earth and Wiki Loves Monuments.

c. Engagement & Usage Analytics: Cross-referencing viewership trends (via Topviews, Massviews, and Wikistats) with editing activity (20-28 active editors) to highlight demand-versus-coverage disparities.

d. Systemic Bias Review: Investigating gender representation gaps, rural community coverage, subject-matter imbalances (e.g., men/history dominating over women/science), and source availability constraints.

1.2 Technical Tooling: The Consultants shall utilize PetScan, Wikidata Query Service (SPARQL), Wikimedia REST APIs, Toolforge utilities, Pageviews Analysis, Wikistats, and custom Python/Jupyter data parsing scripts to extract, filter, clean, and visualize all project metrics.

CLAUSE 2.  DELIVERABLES & WORK OUTPUTS

The Consultants shall formally produce and deliver five (5) core project deliverables to WCUGU:

| Deliverable | Title | Core Description & Components |
| --- | --- | --- |
| Deliverable 1 | Gap Mapping Report | Comprehensive inventory of missing/underdeveloped articles, untranslated Luganda gap lists, stub subcategory breakdowns (154 People, 107 Geo, 92 Sports, 69 Buildings), and citation metrics. |
| Deliverable 2 | Priority Matrix & Content Roadmap | Data-driven decision matrix ranking Uganda categories/topics by readership demand, cultural significance, and quality gap severity to guide future edit-a-thons. |
| Deliverable 3 | Commons Audit Report | Quantitative and qualitative assessment of Uganda media files (43,087+ files), category structures (1,936 subcategories), campaign contributions, and media-type distributions. |
| Deliverable 4 | Strategic Recommendations | Actionable guidance covering targeted translation drives, editor retention initiatives, institutional partnerships, peer review systems, and mentorship programs. |
| Deliverable 5 | Code Assets & Documentation | Fully documented, reproducible repository containing Python scripts, Jupyter Notebooks, SPARQL queries, PetScan configurations, and processed datasets. |

CLAUSE 5.  INTELLECTUAL PROPERTY & OPEN LICENSING

5.1 Open Content Licensing: All reports, datasets, figures, matrices, documentation, and written work outputs compiled or created under this Agreement shall become the property of WCUGU upon creation and shall be made publicly available under the Creative Commons Attribution-ShareAlike 4.0 International (CC BY-SA 4.0) license in alignment with global Wikimedia movement principles.

5.2 Open Source Code Assets: All technical scripts, Jupyter Notebooks, SPARQL queries, and data extraction pipelines developed during the project shall be hosted on an open-source public repository (such as GitHub or Wikimedia GitLab) under an OSI-approved open license (MIT or GPL v3).